## Sheet1
Task | Priority | Status | StartDate | End Date | Notes
Undertsanding the Project approach and overview | P0 | Completed | 21-08-2024 | 21-08-2024 | Getting overall idea to do with project
Creating Database structure for microservices | P0 | Completed | 21-08-2024 | 21-08-2024 | Creating the Databases for all the required microservices
undertsanding microservices approach | P0 | Completed | 22-08-2024 | 22-08-2024 | getting an idea how to implement all the microservices
Eureka-Server | P0 | Completed | 22-08-2024 | 22-08-2024 | Creating the Eureka Server and using git as global repository
User_Management_MicroService | P1 | Completed | 23-08-2024 | 23-08-2024 | Creating the User microservice in springboot and check all api in POSTMAN
Staff_Management_Microservice | P1 | Completed | 24-08-2024 | 24-08-2024 | Creating the staff microservice in springboot and check all the API s in POSTMAN
Service_Management_MicroService | P1 | Completed | 24-08-2024 | 25-08-2024 | Creating the Service microservice in the Springboot and check all API'S in POSTMAN
Booking_Management_MicroService | P1 | Completed | 25-08-2024 | 26-08-2024 | Creating the Booking management microservice in the Springboot and check all API'S in POSTMAN
APIGateway | P1 | Completed | 26-08-2024 | 26-08-2024 | Creating the API in the Springboot and check weather all the microservices are registred with the API
JWT-Authentication-Service | P2 | Completed | 26-08-2024 | 27-08-2024 | Make the authentication with spring security in Springboot and check all API's in POSTMAN
Make frontEND with react | P2 | Completed | 28-08-2024 | 28-08-2024 | Making frontend with react for all microservices customize frontend with microservices approach
Test frontEnd with Backend | P2 | Completed | 28-08-2024 | 29-08-2024 | Test frontend with backend and save resukts and outputs in Document
Junit | P2 | Completed | 30-08-2024 | 30-08-2024 | wtote the sample test case by using junit4
GIT implementation | P3 | Completed | 30-08-2024 | 30-08-2024 | submit source code on Github after completion of project
PPT | P3 | Completed | 2024-01-09 | 2024-01-09 | Create PPT for project review
Documentation | P2 | Completed | 2024-01-09 | 2024-01-09 | Making a all output of all mivroservices in spring boot and database tables and all crud operations in post and all flowcharts for uploading